# OOBE 1.0 Milestone Definitions

## Milestone 1: 2/5/99 (Provide co-working environment for MSN)

### Definition:

Provide co-working environment for MSN. Finish the design and framework.

### Tasks to complete:

PM

- Initial design back from UI designers

- UI Spec hand off to dev/test

- PnP resolved

- Screen resolution resolved

- Specs hand off to dev/test for

- dialing,

- error cases,

- pre-configuration

Dev

- Private Daily builds

- Finish interface design for each module.

- WebHost environment

- Configurable URL through INI file so that msn can hit any corp test server.

### Issues:

None.

After milestone 1, we will start to deliver our daily build to MSN.

## Milestone 2: 2/12/99 (Provide the testable platform)

### Definition:

Provide basic navigation through steps, external interface will be available (not fully functional). Fully functional left pane. OPK tool development start. HTML developments start (UI). Dialup checking (Modem, TCP/IP, RAS, tone detection).

### Tasks to complete:

#### Test

- Test plan

PM

- Revised screens back from designers, handoff to dev

- Revised text back from UA, handoff to dev

- Initial usability feedback (based on screenshots)

- Flesh out exact wording for error cases

- Sync up ScotJohn error cases with Autumn actual UI screens

- (Tues AM - PM get OOBE INI format from DEV)

- EOD Weds -- OPK Spec due + understand how it's integrated with existing OPK tools

- EOD  Fri - OPK screenshots

DEV

- Communication manager (Dialing services/ISP file parsing)

- Dialup checks (Modem, TCP/IP, RAS, tone detection).

- Back end ready (EULA, PID, USERINFO, etc)

- Finish left pane HTML development/Interface function.

- Partially functional navigation manager

- OOBEINFO.INI file processing.

- Start OPK tool development.

- Provide external interfaces.

- Functional offline HTMLs for each page.

- Functional right pane.

- Button pane.

- Testing can start as a standalone app.

- Msgsvr32, setupx integration. Open setupx backend for retail/international case.

- MSGSRV / SETUPX should happen by M2 2/12 rather than waiting  until 2/19 since it is a high risk item

- PnP should get fixed or punted by M2- 2/12

- Daily build by Win98 buildlab

- Critical OSR changes (setupx hook)

- Build API service layer in setupx.

- HTML parser for external interface.

### Issues:

- Need to find a HTML developer. Based on what we need to do in oobe, we won't need any system developer level of HTML experts. Web developer who can do DHTML/Scripts should be able to do the job. I am going to meet one candidate tomorrow and will get some more info from other resources (Microcrafts)

- Whether to use existing phonebook or not. If it is simply US/Canada and Japan, we will just extend existing ISP file format.

- OPK tool spec.

- Resolve PNP issues.

- Drop the build to MSN/Passport and Localization team.

We will release external interface spec for MSN or Passport to use.

## Milestone 3: 2/19/99 (Feature complete)

### Definition:

External interface will be fully functional. Integration into Windows bootup process.  Error handling.

### Tasks to complete:

PM

- Product Key follow-up / close

- Usability testing with MSN Feb 17-18

- Revise OPK screenshots

- IE5 customization for OPK

- OEM and ISP docs for external release

DEV

- INS processing/Webgate.

- Fully functional navigation manager.

- Fully functional right pane and button pane.

- Complete offline HTMLs.

- Error handling/HTMLs

- Finish back end implementation.

- ICWCONN1.EXE for after oobe (?)

- MSN integration testing starts.

- Windows bootup testing starts.

- Complete OPK tool.

- Pre-configuration support

- OSR changes complete

- Welcome changes

### Issues:

- MSN test server should be ready at this moment.

- Spec for after-oobe when user didn't signup.

- Need the complete scenario for retail/int’l case.

- Localization starts.

Windows setup will include our binaries and oobe will be part of win98 OSR official build.

## Milestone 4: 3/5/99 (Beta RC0)

### Definition:

UI freeze. Majors bug fixes and stabilize the product. Fully merge with Win98 OSR1.

### Tasks to complete:

- Bug fix. No more feature work for beta.

- Minimum UI changes

- OPK tool

- OEM bootcamp starts

Using OPK tool, we should be able to complete OEM production scenario.

### Issues:

- MSN real production server ready.

## Milestone 5: 3/12/99 (Beta RTM)